Difference between Risk and Issue in Project Management

In project management, the simplest distinction is:

Risk = something that might happen.
Issue = something that has already happened.

| Aspect | Risk | Issue |
| --- | --- | --- |
| Meaning | Potential future event | Current/actual problem |
| Timing | Has not happened yet | Already happened |
| Impact | May affect project | Is affecting the project |
| Management | Risk mitigation/response | Issue resolution |
| Owner | Risk owner | Issue owner |
| Example | “The database migration may take longer than planned.” | “The database migration is 3 days late.” |
| Typical action | Avoid, mitigate, transfer, accept | Resolve, escalate, workaround |
| Tracking | Risk Register | Issue Log |

### Example from your SQL migration project

Risk:

There is a possibility that the existing SQL Agent jobs may not be fully compatible with Azure SQL Managed Instance, which could delay migration.

This is a risk because the problem has not necessarily occurred yet.

Issue:

5 SQL Agent jobs failed during testing on Azure SQL Managed Instance because they depend on unsupported PowerShell commands.

This is an issue because the problem has actually occurred.

### How a Risk becomes an Issue

A useful way to remember it:

PROJECT MANAGEMENT

│

▼

┌─────────────────┐

│      RISK       │

│ "Might happen"  │

└────────┬────────┘

│

Risk occurs

│

▼

┌─────────────────┐

│      ISSUE      │

│ "Has happened"  │

└─────────────────┘

### Risk Register vs Issue Log

Risk Register might contain:

Risk: Linked server incompatibility

Probability: Medium

Impact: High

Risk Score: High

Mitigation: Test all linked servers before migration

Owner: DBA Lead

Issue Log might contain:

Issue: Linked Server FINANCE01 failed after migration

Impact: Finance reports unavailable

Severity: High

Action: Reconfigure provider/authentication

Owner: DBA Lead

Due Date: 25-Aug-2026

Status: In Progress

### Easy interview answer

If someone asks “What is the difference between a risk and an issue?”, a strong answer is:

A risk is an uncertain event that may impact the project in the future, while an issue is a problem that has already occurred and requires action. Risks are managed proactively through mitigation and contingency planning; issues are managed reactively through resolution and escalation.

Contingency plan

A contingency plan is a predefined backup plan for what you will do if a known risk actually occurs.

### Simple definition

Contingency Plan = “If this risk happens, what will we do?”

For example, in your SQL Server → Azure migration:

Risk:
The migration of a 1 TB database may take longer than the planned downtime window.

Contingency plan:
If the migration is not completed within the agreed downtime window, stop the cutover, keep the existing SQL Server VM as the production system, roll back the application connection changes, and reschedule the final migration after resolving the bottleneck.

### Risk → Mitigation → Contingency

These three are often confused:

| Term | Meaning | Example |
| --- | --- | --- |
| Risk | What might happen? | Migration may exceed the downtime window |
| Mitigation | What will we do beforehand to reduce the probability/impact? | Perform a rehearsal migration and optimize the migration process |
| Contingency | What will we do if it actually happens? | Roll back to the existing SQL Server VM |
| Issue | What has actually happened? | Migration exceeded the downtime window |

### Example for your project

| Risk | Mitigation | Contingency |
| --- | --- | --- |
| Linked server doesn't work on MI | Test all linked servers before cutover | Keep source SQL Server active and revert affected workload |
| SQL Agent job fails | Test jobs in UAT | Manually execute critical job / restore source execution |
| Paginated reports fail | Test all critical RDLs | Point reports back to source SQL Server |
| Migration takes too long | Conduct rehearsal + pre-stage data | Abort cutover and continue on existing VM |
| Performance is poor | Baseline current SQL performance | Scale MI compute tier |
| Data synchronization fails | Monitor continuous sync | Perform final backup/restore and reschedule cutover |
| Application cannot connect | Test connection strings beforehand | Roll back application configuration |

### In project management

A good contingency plan should define:

- Trigger — What tells us the risk has occurred?

- Action — What exactly will we do?

- Owner — Who makes the decision?

- Time limit — When do we activate it?

- Resources — What people/tools are needed?

- Communication — Who needs to be informed?

For example:

Risk:

Migration downtime exceeds 4 hours

Trigger:

Migration is not complete after 3 hours

Contingency:

1. Stop migration

2. Validate source SQL Server

3. Keep applications on source

4. Roll back DNS/connection changes

5. Notify stakeholders

6. Analyze migration bottleneck

7. Reschedule cutover

Owner:

Migration Lead / DBA

Maximum decision time:

3 hours after cutover begins

One-line interview answer:

A contingency plan is a predefined response that we execute when a known risk occurs, to minimize its impact on the project's scope, schedule, cost, or quality.

mitigation plan vs contingency plan

The key difference is when you act.

Mitigation plan = What will we do to reduce the chance or impact of a risk?
Contingency plan = What will we do if the risk actually happens?

|  | Mitigation Plan | Contingency Plan |
| --- | --- | --- |
| Purpose | Reduce probability or impact | Respond after the risk occurs |
| Timing | Before the risk occurs | After the risk occurs |
| Approach | Proactive | Reactive/pre-planned |
| Key question | “How can we prevent or reduce it?” | “What will we do if it happens?” |
| Example | Test migration before production | Roll back to the old SQL Server |
| Cost | Usually preventative | Usually recovery/response |

Example from your SQL Server migration

Risk:
Azure SQL Managed Instance migration may cause paginated reports to fail.

Mitigation plan:

- Test all critical paginated reports in UAT.

- Validate database connectivity.

- Test RDL parameters and queries.

- Test linked servers.

- Perform a pilot migration.

- Fix compatibility issues before production.

➡️ Goal: Reduce the likelihood and impact of failure.

Contingency plan:

- If critical reports fail after cutover, stop the migration.

- Keep the original SQL Server VM available.

- Redirect reports/applications back to the source.

- Restore the previous configuration.

- Investigate and fix the problem.

- Schedule another cutover.

➡️ Goal: Minimize the impact after the risk becomes a reality.

Easy way to remember

RISK

│

┌──────┴──────┐

│             │

▼             ▼

MITIGATION     CONTINGENCY

"Prevent /     "If it happens,

reduce it"     what next?"

│             │

▼             ▼

BEFORE        AFTER

Another simple example

Risk: Key team member may become unavailable.

Mitigation: Cross-train another team member.

Contingency: If the person becomes unavailable, assign the trained backup resource.

Interview answer

Mitigation is a proactive action taken to reduce the probability or impact of a risk. Contingency is a predefined response that is activated if the risk actually occurs. In simple terms, mitigation is “prepare to prevent or reduce,” while contingency is “prepare to respond.”

mitigation plan vs contingency plan

The key difference is when you act.

Mitigation plan = What will we do to reduce the chance or impact of a risk?
Contingency plan = What will we do if the risk actually happens?

|  | Mitigation Plan | Contingency Plan |
| --- | --- | --- |
| Purpose | Reduce probability or impact | Respond after the risk occurs |
| Timing | Before the risk occurs | After the risk occurs |
| Approach | Proactive | Reactive/pre-planned |
| Key question | “How can we prevent or reduce it?” | “What will we do if it happens?” |
| Example | Test migration before production | Roll back to the old SQL Server |
| Cost | Usually preventative | Usually recovery/response |

### Example from your SQL Server migration

Risk:
Azure SQL Managed Instance migration may cause paginated reports to fail.

Mitigation plan:

- Test all critical paginated reports in UAT.

- Validate database connectivity.

- Test RDL parameters and queries.

- Test linked servers.

- Perform a pilot migration.

- Fix compatibility issues before production.

➡️ Goal: Reduce the likelihood and impact of failure.

Contingency plan:

- If critical reports fail after cutover, stop the migration.

- Keep the original SQL Server VM available.

- Redirect reports/applications back to the source.

- Restore the previous configuration.

- Investigate and fix the problem.

- Schedule another cutover.

➡️ Goal: Minimize the impact after the risk becomes a reality.

### Easy way to remember

RISK

│

┌──────┴──────┐

│             │

▼             ▼

MITIGATION     CONTINGENCY

"Prevent /     "If it happens,

reduce it"     what next?"

│             │

▼             ▼

BEFORE        AFTER

### Another simple example

Risk: Key team member may become unavailable.

Mitigation: Cross-train another team member.

Contingency: If the person becomes unavailable, assign the trained backup resource.

### Interview answer

Mitigation is a proactive action taken to reduce the probability or impact of a risk. Contingency is a predefined response that is activated if the risk actually occurs. In simple terms, mitigation is “prepare to prevent or reduce,” while contingency is “prepare to respond.”