## Instructions
# | Field | Content
1 | Transition Activity Description | Provide a clear, concise description of the knowledge transfer or handover activity. Example: Application architecture walkthrough, Incident management process KT, Access provisioning demo.
2 | Type | Specify the category or type of transition activity — e.g., Knowledge Transfer (KT), Documentation, Shadow Support, Reverse Shadow, Tool Access, etc.
3 | Person Responsible for Plan and Confirming Complete | Enter the individual accountable for ensuring the activity is planned, executed, and marked complete. This person validates that acceptance criteria for transition are met.
4 | Facilitator / Content Owner | Mention the person or SME delivering the knowledge transfer or providing the content. Often, this is the project resource handing over knowledge.
5 | Complete by Date | Indicate the target completion date for the transition activity. Ensure this is realistic and aligns with the overall transition timeline.
6 | Status | Track progress using consistent status options such as Not Started / In Progress / Completed / Delayed. Update this regularly to reflect accurate progress.
7 | Who was KT provided to? | List the names or roles of individuals or teams who received the knowledge transfer. Helps verify that the intended support audience is covered.
8 | Recording Link | Provide the URL or shared drive location where the session recording is stored. Ensure access permissions are appropriately managed.
9 | Reference Docs / Links | Add links or file paths to key supporting documents, such as user guides, SOPs, runbooks, or configuration manuals shared during the transition.
10 | Notes | Capture any additional remarks, observations, or follow-up actions related to the transition activity — e.g., pending access setup, session rescheduled, additional session required.

## Support Transition Plan
Elgi Equipment
S.No. | Transition Acitivity Description | Type | Person Responsible for Plan and Confirming Complete | Facilitator / Content Owner | Complete by Date | Status | Who was KT provided to? | Recording Link | Reference Docs / Links | Notes

## Lookups (hidden)
Type | Status
Email Notification | Not Started
Documentation | In Progress
KT / Handoff Meeting | Complete