## Instructions
# | Field | Content
1 | Focus Area | Specify the key area or activity being validated for closure (e.g., Deliverables Sign-off, Financial Closure, Knowledge Transfer, Documentation Archival, Lessons Learned). Each row should represent one major closure requirement.
2 | Status | Capture the current state of completion for each focus area. Recommended values: Not Started, In Progress, Completed, N/A. Ensure the status accurately reflects actual progress based on supporting evidence.
3 | Comments | Provide concise remarks or observations related to the closure activity — e.g., pending actions, dependencies, or confirmation notes. Use this field to document any deviations, partial completions, or follow-up actions required post-closure.

## Closure check list
Elgi Equipment
# | Focus Area | Status | Comments
1 | Transition to Support Completed and signed-off by Operations Teams
2 | Open Defects are mitigated.
3 | Requirements Traceability Matrix completed to ensure project delivered all requirements
4 | Verify all invoices have been received and approved. Budget Tracker and PPM Project should be updated with ALL actual spending totals.
5 | If internal project labor is being capitalized the PM ensures all time sheets have been submitted and approved.
6 | ALL project documentation should be moved into the Project Documentation Folder.
7 | Lesson Learned Completed with project team and Steering Committee (include executive summary version to be shared with IT Leadership Team during Portfolio Review meeting)
8 | Conduct final Steer Co meeting using standard Steering Committee presentation template and minutes confirming their agreement to close the project.
9 | Project Satisfaction Survey’s sent to Steer Co
10 | IT Project Portfolio Manager quality assures and agrees that all requirements have been met to formally close the project.