## Sheet1
Sno | Requirement | Description | Task Category | Task Type | Task Index | Tasks Required | Prerequisites | RoadBlocks Identified | Remarks | Requestor | Responsibility | Status | Requirement Discussion Date | Task Creation Date | Task Start Date | Estimated Date | Completion Date
1 | North America Sales Data Retrieval and Automation | Consolidated Sales Data shared via mail to Finance Team by the User :Nicole, is currently considered for Dashboard update in Finance Team | SOP | Independent | 1 | To Identify how the Sales numbers are generated by Nicole and SOP required for this data generation | Finance Team to discuss with Nicole on this and clarity will be provided | 12-12-2025 : No Information available at User end as How the Consolidated Sales Numbers are Generated by Nicole as Data Mismatch observed when attempted to match with LN Session :txsli3405m000 during the Teams Meeting : "Project Kickoff : Sales, Margin, Expense, and Inventory Consolidation Program" 02-01-2026 : Discussed Following in Teams Meeting 1.To fetch Manually the Raw data ouput file downloaded from the above mentioned LN Session and note down the deviations for NOV-25 to proceed further 2. Above LN Session Data Output will not provide all the required attributes to align with Detailed Data Dump Currently available for India Region(Eg : LN Session output will not contain Order Qty, Invoice Qty) | Corrective Action : Alternate approach of Considering Sales data from LN Invoice 360 is done | Data Team | Finance Team | Completed | 2025-12-12 | 2025-12-23 | 2025-12-12 | 2025-12-30 | 2026-01-06
1 | North America Sales Data Retrieval and Automation | Consider the Sales from LN Session : txsli3405m000 available from Infor LN | SOP | Independent | 1.1 | NA Business Data Generation Procedure Step 1: Download Raw Data for the Month from txsli3405m000 Date and time to be 12 am to 11.59 pm Step 2: Exclude S26 - Proforma Invoices.Column Name Document (Column N) First 3 Characters = S26 Step 3: Create a new colum in base file called "Direct/Inter Co" . Logic: IF BP Code begins with I or G Inter Co else Direct Step 4: Lookup the Product Line # field with the Item group in the lookup master and pick the item group for the vertical Step 5: Pivot 1 - By Entity is total Sales Less IC Less Freight = Net Sales Step 6: Pivot 2 - Item Category wise Breakdown in '000 |  | 1. Since LN Session Output is generated during Runtime and not available as a physical Table Output, The logic needs to be Rebuilt in BI to replicate the same Session Output 2. Since this session was not developed by ELGI IT Team and no documentation on the session build is currently available, it is currently onholded | Corrective Action : Alternate approach of Considering Sales data from LN Invoice 360 is done | Finance Team | Data Team | Completed | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06
1 | North America Sales Data Retrieval and Automation | Consider the Sales from LN Session : txsli3405m000 available from Infor LN | Feasibility Check | Independent | 2 | File Import of this session Data from LN on Scheduled Basis | Data Team to get guidance from LN IT Sales Team for Operational feasibility | 30-12-2025 : Checked with Prakash and observed that automation on File Import of GL Session Data is not Feasible. Alternate Solution : The LN Code used to Build the GL Session for NA is shared by Prakash. Further on, ETL Activity and Data Modelling has to be Built Up in BI which requires considerable Effort and Time which is to be Estimated after LN Code Study 02-01-2026 : Information on Data Modelling and Logic used to build this Session is not available without which the same Business Data cannot be generated in BI. This Issue has also been Informed with Ravi Chandra Raju via Teams Meeting call. Clarity not arrived yet to proceed further | Corrective Action : Alternate approach of Considering Sales data from LN Invoice 360 is done | Data Team | LN IT Sales Team | Completed | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23
1 | North America Sales Data Retrieval and Automation | To Share the Raw Sales Transaction dump for Jan and Feb 2026 to arrive a new logic by Finance to match with the Session Output | SOP | Independent | 3 | Raw Sales dump for Jan and Feb 2026 to be shared to Finance |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
1 | North America Sales Data Retrieval and Automation | Based on the Raw Data Reconciliation, Base source to be considered for all the sales reports is Invoice 360 with the following conditions 1. S19 – Suppier/Customer Claims Removal 2.Instalment invoices Removal 3. Service Contracts Data addition. | SOP | Independent | 4 | Tran type : S19 to be eliminated from Invoice 360 sales transactions |  |  |  | Finance Team(Manikumar) | Data Team(Vasanth) | Completed | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-06 | 2026-04-06
1 | North America Sales Data Retrieval and Automation | Based on the Raw Data Reconciliation, Base source to be considered for all the sales reports is Invoice 360 with the following conditions 1. S19 – Suppier/Customer Claims Removal 2.Instalment invoices Removal 3. Service Contracts Data addition. | SOP | Independent | 5 | Instalment invoices removal after getting implemented in LNà Logic to remove those invoices can be received from LN Team after CR implementation. | Logic to be shared from LN for removal of Instalment Invoices |  |  | Finance Team(Manikumar) | LN Team (Prem) | Completed | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-06 | 2026-04-06
1 | North America Sales Data Retrieval and Automation | Based on the Raw Data Reconciliation, Base source to be considered for all the sales reports is Invoice 360 with the following conditions 1. S19 – Suppier/Customer Claims Removal 2.Instalment invoices Removal 3. Service Contracts Data addition. | SOP | Independent | 6 | Service Contracts Data Inclusion : Initial Invoice Transactions made on Service contracts will be available in Invoice 360 and it should not be considered. Instead, “Revenue Recognition” process will be carried out in LN for those invoices and get added to Sales GL. But the updates on those invoices(after revenue recognition process) will not be available in Invoice 360. | Manikumar Suggessted to discuss with Gokul on how it is currently considered in USA Sales Report in Power BI | Service Contract Invoice value Mismatch for Pattons (3140) and MAS (3150) Observed that source session considered by Finance and Source table referred by Data Team for fetching Service Contract data are different. As per mail dated :23 March 2026 17:03 : Service Contracts Data Inclusion : Initial Invoice Transactions made on Service contracts will be available in Invoice 360 and it should not be considered. Instead, “Revenue Recognition” process will be carried out in LN for those invoices and get added to Sales GL. But the updates on those invoices(after revenue recognition process) will not be available in Invoice 360. To be discussed with Gokul on how it is currently considered in USA Sales Report in Power BI. After Internal discussion with Gokul, Added the Service Contracts details available from LN Table : LN_TSCTM400 with Filter Condition : STIN=20 27-04-2026: Observed that the above table does not include all Service Contract Transactions.Communicated via Mail to Joseph(LN ERP Team) to find out the root cause. 12-05-2026: Communicated to Gokul(LN ERP) to address the missing Service Contract invoices provided from venkatesh(Finance) | LN ERP Team to revert on the latest followup mail sent on 13-05-2026 from Vasanth | Finance Team(Manikumar) | Data Team(Vasanth) | WIP | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-06
1 | North America Sales Data Retrieval and Automation | Service Contracts Data Validation | Testing | Sequential | 7 | Unit Testing with sample data with different Test Cases | After Closure of Task Index :6 |  |  | Finance Team | Data Team(Vasanth) | On Hold | 2025-12-12 | 2026-03-31 | 2026-04-02 | 2026-04-06
1 | North America Sales Data Retrieval and Automation | Service Contracts Data Validation | Testing | Sequential | 8 | User Acceptance Testing and confirmation on Data Correctness and Integrity | After Closure of Task Index :7 |  |  | Data Team(Vasanth) | Finance Team(Saurabh) | On Hold | 2025-12-12 | 2026-03-31 | 2026-04-02 | 2026-04-06
2 | Europe Sales Data Retrieval and Automation | GL Session : txsli3405m000 available from Infor LN is not extended for Europe and hence the Sales numbers are shared via mail to Finance Team by the User: Luca | SOP | Independent | 9 | To Identify how the Sales numbers are generated by Luca and SOP required for this data generation | 1. Finance Team(Ishwetha) shared the SOP provided by Luca on this and Data Generation to be carried out based on this SOP 2. Finance Team(Karthik) shared the alternate Session Code : txsli3410m000 to be considered as a source for Business Data Generation with the SOP Provided | Few Clarifications requested via Mail by Data Team(Vasanth) to be addressed by Finance Team (Karthik) | Corrective Action : Alternate approach of Considering Sales data from LN Invoice 360 is done | Data Team | Finance Team(Karthik) | Completed | 2025-12-12
2 | Europe Sales Data Retrieval and Automation | Access Required to the existing Power BI Report for ELGi Europe to Finance Team for the feasibility check | Access | Independent | 10 | Power BI Access for ELGi Europe Workspace to be Provided |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2025-12-30 | 2025-12-30 | 2025-12-30
3 | Rotair Sales Data Retrieval and Automation | GL Session : txsli3405m000 available from Infor LN is not extended for Rotair and hence the Sales numbers are shared via mail on weekly basis to Finance Team by the User: Luca | SOP | Independent | 11 | To Identify how the Sales numbers are generated by Luca and SOP required for this data generation | 1. Finance Team(Ishwetha) shared the SOP provided by Luca on this and Data Generation to be carried out based on this SOP 2. Finance Team(Karthik) shared the alternate Session Code : txsli3410m000 to be considered as a source for Business Data Generation with the SOP Provided | Few Clarifications requested via Mail by Data Team(Vasanth) to be addressed by Finance Team (Karthik) | Corrective Action : Alternate approach of Considering Sales data from LN Invoice 360 is done | Data Team | Finance Team(Karthik) | Completed | 2025-12-12 | 2025-12-23
4 | Pulford Sales Data Retrieval and Automation | Data Retrieved from the Pulford Server URL : http://pulford-nav.jigsaw.com.au/Reports/Pages/Folder.aspx Report Name : SalesReportByDepartments_Combined | Source Data Fetching | Sequential | 12 | To Identify the SPOC for getting the required Inputs | Data Team(Krishna) communicated via Mail to LN IT Sales Team for SPOC from Pulford IT Support |  | SPOC : Dipali Nimani From Pulford | Data Team(Krishna) | LN IT Sales Team | Completed | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23
4 | Pulford Sales Data Retrieval and Automation | Data Retrieved from the Pulford Server URL : http://pulford-nav.jigsaw.com.au/Reports/Pages/Folder.aspx Report Name : SalesReportByDepartments_Combined | Source Data Fetching | Sequential | 13 | 1. Access the Report in the Pulford Portal and Feasibility Study for Data Integration 2. Observed that Calculated Columns are referred in the Report named: SalesReportByDepartments_Combined It is not feasible to Integrate History Data based on this Report Alternate Solution: Report Data Owner to Provide the List of tables and Modelling used to build this Report 06-01-2026: Had a teams Discussion with Pulford SPOC(Dipali) and requested the following 1. List of Tables, Data Modelling and Logic to build the numbers matching to the above mentioned Pulford Report 2. Required list of attributes for building the Sales dump. |  | As of 06-01-2026 :Finance Team has Shared the Credential to Access the Report and Observed that Calculated Columns are referred in the Report named : SalesReportByDepartments_Combined It is not feasible to Integrate History Data based on this Report Alternate Solution: Report Data Owner to Provide the List of tables and Modelling used to build this Report | List of Tables , Logical Relationships and Data exclusion logics are shared from the user end | Data Team | Pulford SPOC(Dipali) | Completed | 2025-12-12 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28
4 | Pulford Sales Data Retrieval and Automation |  | Source Data Fetching | Sequential | 14 | Report Data Owner to Provide the List of tables and Modelling used to build this Report |  |  |  | Data Team | Pulford SPOC(Dipali) | Completed | 2025-12-12 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28
4 | Pulford Sales Data Retrieval and Automation |  | Source Data Fetching | Sequential | 15 | ETL Activity on the List of Tables collected from Task Index : 14 | Task Index 14 to be completed |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2025-12-31
4 | Pulford Sales Data Retrieval and Automation |  | Source Data Fetching | Sequential | 16 | Code Development to replicate the Pulford Report Output | Logic required for categorizing the Pulford sales details into respective categories shared in the Template |  |  | Data Team(Vasanth) | Pulford SPOC(Dipali) | Completed | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2025-12-31
4 | Pulford Sales Data Retrieval and Automation |  | Source Data Fetching | Sequential | 17 | Unit Testing with sample data with different Test Cases | Task Index 16 to be completed |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2025-12-31
4 | Pulford Sales Data Retrieval and Automation |  | Source Data Fetching | Sequential | 18 | User Acceptance Testing and confirmation on Data Correctness and Integrity | Task Index 17 to be completed |  |  | Data Team(Vasanth) | Pulford SPOC (Chandra Sekar) | Open | 2025-12-12 | 2025-12-23 | 2025-12-23 | 2025-12-31 | 2025-12-31
4 | Pulford Sales Data Retrieval and Automation |  | SOP | Independent | 19 | Currently, ATS Project Numbers are received via mail from Regional Finance Team and it has to be automated | Finance Team(Venkat) to provide the Process feasibility for capturing this data directly from the System by collaborating with the Respective Data Owner |  |  | Data Team(Vasanth) | Finance Team(Venkat) | Open | 2025-12-12 | 2025-12-23
5 | Dashboard Data Update Process | Region Level Consolidated sales numbers are considered | Code Development | Independent | 20 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-12 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Day wise Trend of sales Numbers to be displayed as per the User Dashboard Template | Code Development | Independent | 21 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-12 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Data Sourced to this Board Review will be out of following transactions 1. Frieght Transactions 2. Intercompany Transactions | Code Development | Independent | 22 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-12 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Elgi Australia, Data is Sourced from BI Report : COSEA Sales Performance USD Column Considered : Column J (Current Month Actuals) Rows Considered : Rows 7 and 18 (PAG and AA Sales) | Code Development | Independent | 23 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-12 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For SEA, Data is Sourced from BI Report : COSEA Sales Performance USD Column Considered : Column J (Current Month Actuals) Rows Considered : Rows 86,101,117,183 (Indonesia,Thailand ,SEA Others, Malaysia) | Code Development | Independent | 24 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For India, Data is Sourced from BI Report : ELGi Sales Performance Column Considered : Column G (Current Month Actuals) Rows Considered : Rows 17,40,49,58,64,67 (After Sales, Channel,Direct,RLY,WW,C&M) For OFSAC : Consider the Rows: 54,55,57 (or the DPSTName with OFSAC) and exclude this sales from Direct | Code Development | Independent | 25 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For SAAME, Data is Sourced from BI Report : ELGi Sales Performance Column Considered : Column G (Current Month Actuals) Rows Considered : Rows 78,84 (Africa), Row 92(ATS), Rows 94,104(Gulf), Rows 116,122(Gulf), Rows 129,136(SA) | Code Development | Independent | 26 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Vacuum, Data is Sourced from BI Report : ELGi Sales Performance Column Considered : Column G (Current Month Actuals) Rows Considered : Row 9 | Code Development | Independent | 27 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Intercompany Sales(Subsidiary Sales), Data is Sourced from BI Report : ELGi Sales Performance Column Considered : Column G (Current Month Actuals) Rows Considered : Row 12 | Code Development | Independent | 28 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Brazil Sales, Data is Sourced from Power BI Workspace : Brazil Power BI Report : Brazil_Sales Filter Applied: 1. Column Named 'Type', Data to be Filtered Out : Type starts with "Remessa" 2. Returns Value obtained from Returns page to be seperated Column Considered after exporting to Excel : Column AA (Total) | Code Development | Independent | 29 | To be addressed in Code Development phase |  | 1. Observed that Brazil Report Data downloaded on 18 Mar 2026 for Nov-25 Period shows 4390458.53 with respect to the data downloaded by Ishwetha(Finance Team) (during Teams Meeting : Sales Dashboard - Internal Walkthrough) on 24-Dec-2025 for Nov-25 Period shows 3656550 Note: Filter applied on both the cases : Type <> Remessa 2. The base data for this report is built from Receipt Transactions(and not from Sales Transactions as used for India Regions) where Sales is picked up from the following Categories 1. Purchase Receipts 2. Purchase Return Receipts 3. Sales Receipts 4. Sales Return Receipts Hence it cannot be appended with Other Regions Sales Details |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23
5 | Dashboard Data Update Process | For ATS, Data is Sourced from BI Report : ATS Daily Performance Column Considered : Column J (Current Month Actuals) Rows Considered : Row 53 Filter Condition : 1. Seperate the Scrap Sales value available at Row 46 in Column J 2. Seperate the FRT Sales value available at Row 50 in Column J 3. Separate the Intercompany sales value available in Elgi-group Sales Sheet Row no:8 in Column J | Code Development | Independent | 30 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Rate Conversion, Consider the Rate which is fixed during Budgeting at the start of the Financial Year, for Conversion of Actuals across the Financial year | Master Data Process | Independent | 31 | Master Template to be developed and Shared to the User through Sharepoint |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Consider the Respective Home Currency Value for each regions and display the Currency Considered | Code Development | Dependant | 32 | To be addressed in Code Development phase | Any Task Index between 23-30 to be completed |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | For Grand Total Calculation, 1. Consider the INR Conversion Rate updated by the user via sharepoint(Task Index :30) 2. Intercompany Sales value not to be considered for this calculation | Code Development | Dependant | 33 | To be addressed in Code Development phase | Any Task Index between 23-30 to be completed |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Provision required to manually Update the Budget,Forecast Numbers in to the System Note: Forecast numbers are subject to Revision of 3 times in a month by Sales Team. Template should accommodate all the Revisions | Master Data Process | Independent | 34 | Master Template to be developed and Shared to the User through Sharepoint |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Running Calculation of Numbers required based on Month Selection. Running Period will be 12 Months from the Selected Month in Power BI Report | Code Development | Dependant | 35 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | GL Versus Sales Data Linking Logic to analyze the List of Transactions for the Consolidated Numbers shown in the Dashboard | Code Development | Independent | 36 | To be addressed in Code Development phase | To Get the Logic for relationship between GL and Sales Transactions |  |  | Data Team | Finance Team | Cancelled
5 | Dashboard Data Update Process | Sales Data Reconciliation with Ledger will be done during the Month end. Provision to update the Recon Data/Adjustment Entries for each month to be given to the User | Master Data Process | Independent | 37 | Master Template to be developed and Shared to the User through Sharepoint |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Adjusted Numbers by the users will be displayed as a separate field in the Power BI Report. Adjusted MTD column will be sum of Actual Numbers from the System and Adjusted Numbers by the Users | Code Development | Dependant | 38 | To be addressed in Code Development phase | Task Index 36 and 37 to be completed |  |  | Finance Team | Data Team | Open | 2025-12-12 | 2025-12-23
5 | Dashboard Data Update Process | MTD across all the Running 12 Months required in a separate Sheet in Power BI | Code Development | Independent | 39 | To be addressed in Code Development phase |  |  |  | Finance Team | Data Team | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28
5 | Dashboard Data Update Process | Calendar Proportion and Achievement % Calculation | Code Development | Dependant | 39 | To be addressed in Code Development phase | To identify how the Holidays are excluded in addition to Weekoffs i.e how to track the National Holidays from the System |  |  | Data Team | Finance Team | Cancelled | 2025-12-12 | 2025-12-23
5 | Dashboard Data Update Process | Personna Level Access to the Dashboard based on Region Level Control | Master Data Process | Independent | 40 | Master Template to be developed and Shared to the User through Sharepoint |  |  |  | Finance Team | Data Team(Vasanth) | Completed | 2025-12-12 | 2025-12-23 | 2026-01-12 | 2026-02-28 | 2026-02-28

## Sheet2 (hidden)
Open
WIP
Unit Testing
User Acceptance Testing
Completed
Cancelled
On Hold