## Sheet1
Executive Summary | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | a | a
PY Sales | r | r | r | r | r | r | r
Additional Notes:
In SEA, Company Code-490 Sales are grouping under Malaysia instead of SEA- VPS. It should be group under SEA-VPS since it is billing under HO
In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard
In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
Daily Sales Summary | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | a | a
PY Sales | r | r | r | r | r | r | r
Additional Notes:
Why CY_MTD numbers not tallied CY FTM numbers since the month has been completed ?
In SEA, Company Code-490 Sales are grouping under Malaysia instead of SEA- VPS. It should be group under SEA-VPS since it is billing under HO
In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard
In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
Month-on-Month | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | a | a
Additional Notes:
In SEA, Company Code-490 Sales are grouping under Malaysia instead of SEA- VPS. It should be group under SEA-VPS since it is billing under HO
In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard
In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
Month& Day View | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | a | a
Additional Notes:
In SEA, Company Code-490 Sales are grouping under Malaysia instead of SEA- VPS. It should be group under SEA-VPS since it is billing under HO
In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard
In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
Details (Sales Register) | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | r | a
Product view | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | a | a | r | a
PY Sales | r | r | r | r | r | r | r
Additional Notes:
Only total value & qty has been considered- No breakup has been provided for all the regions.
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard
In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn
In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard
Product view | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | r | r | r | r
PY Sales | r | r | r | r | r | r | r
Additional Notes:
Only India has been updated. RoW has not been updated yet
In the updated RoW, kindly let us know what and all regions have been considered and for the same 180 Mn, need to provide the further levels breakup which has not been done
Product view | ISAAME + SEA | Europe | USA | Brazil | Australia | ATS | Sales to subsidiaries
CY Sales | a | r | r | r | r | r | r
PY Sales | r | r | r | r | r | r | r

## Sheet2
Sno | PageName/Region | Issue Identified | Status | Issue Communicated Date | Completion Date | Corrective Action | Remarks
1 | All Pages | In SEA, Company Code-490 Sales are grouping under Malaysia instead of SEA- VPS. It should be group under SEA-VPS since it is billing under HO | Completed | 2026-04-06 | 2026-04-13 | Data Mapping Corrected
2 | All Pages | In brazil, CY numbers not correct. The Numbers which was arrived as per the logic of Vasudevan is different from the numbers provided in the sales dashboard | Completed | 2026-04-06 | 2026-04-13 | Sales Return was misinterpreted. Clarification provided on fetching the Sales return value
3 | All Pages | In Australia YTD, Interco sales mentioned in dashboard is 221 Mn whereas as per Daily Sales file, it is 234 Mn and for Pulford, it is mentioned as 1105 Mn in the sales dashboard whereas as per daily sales, it is mentioned as 1103 Mn | Open | 2026-04-06 |  | As of 20-04-2026 1.Observed that Australia YTD is matching. 2. For Pulford, Line wise data comparision needs to be done between BI and Pulford Data Source to find out the difference. 21-04-2026 Venkat clarified the Pulford data deviation to Chandru. Chandru to revert after data validation
4 | All Pages | In ATS, Scrap Sales, Supplier Sales, Freight & Intercompany sales to be removed which has not been done in the dashboard | Completed | 2026-04-06 | 2026-04-13 | Filter Logic Issue Corrected
5 | Product View | Only total value & qty has been considered- No breakup has been provided for all the regions. | Completed | 2026-04-06 | 2026-04-13 | Clarification provided on the Data Interpretation as Categorization is based on S & OP Input
6 | Geography View | Only India has been updated. RoW has not been updated yet | Completed | 2026-04-06 | 2026-04-14 | USA and Europe Data Integrated
7 | Geography View | In the updated RoW, kindly let us know what and all regions have been considered and for the same 180 Mn, need to provide the further levels breakup which has not been done | WIP | 2026-04-06 |  | As of 20-04-2026 : Data Mapping for Europe is not available. To be Provided from Finance 21-04-2026 Karthik to perform data validation for Europe and provide the Mapping logic 27-04-2026 Karthik completed the data validation and communicated via mail that all invoices are matching for Europe and Rotair and informed that service contract invoices are missing in the Dashboard
8 | All Pages | USA Sales not available for Pattons,MAS and Others | Completed | 2026-04-14 | 2026-04-15 | Data mapping Issue Corrected
9 | All Pages | USA to Intercompany sales to be considered based on Custcode starts with I and G | Completed | 2026-04-14 | 2026-04-15 | Logic updated
10 | All Pages | Item Category Classification to be corrected in S & OP, Non ELGI Item code master to be Integrated in the Sales Dashboard | Open | 2026-04-14
11 | All Pages | ATS Supplier Sales not to be considered | Completed | 2026-04-14 | 2026-04-15 | Logic updated
12 | All Pages | ATS Sales with Blank Category is eliminated. It should be considered | Completed | 2026-04-21 | 2026-04-21 | Code Correction done
13 | All Pages | Currency Rate to be considered from the Master data provided from Finance Team for the Following Regions Australia,Indonesia,Malaysia, USA,Europe and Brazil | Completed | 2026-04-21 | 2026-04-21 | Currency Rate considered from Finance instead of LN Currency Rate Master Table
14 | Product View | ItemCategory and Productgroup classification is not available for the Following Regions 1. ATS 2. Sales to Subsidiary | Completed | 2026-04-21 | 2026-04-21 | 1. For ATS, No Master is maintained in S & OP 2. For Sales to Subsidiary, Data is fetched based on ItemCode Lookup instead of Region and Itemcode Lookup as followed for other regions. The reason is , S & OP Master is not maintained for Subsidiary Sales from ELGi HO
15 | All Pages | PY Column contains blanks values for FY 2025-26 | Completed | 2026-04-21 | 2026-04-21 | Code Correction done
16 | Geography View | Area / Country not updated for USA, Europe and Pulford. | Open | 2026-04-21 |  | Data Mapping logic for respective Area/Country is not available
17 | All Pages | GTM Invoices Posted on Apr 2026 is showing in Mar 2026 in BI. Test case Invoice : 3110 / S10 / 24003279 | Completed | 2026-04-24 | 2026-04-24 | TimeZone difference corrected
18 | All Pages | Customer Claim Orders for ELGI USA to be removed | Completed | 2026-04-24 | 2026-04-24 | Orderno starting with CC is removed form the Sales Transactions
19 | All Pages | Service Contract Invoice value Mismatch for Pattons (3140) and MAS (3150) | Open | 2026-04-24 |  | Observed that source session considered by Finance and Source table referred by Data Team for fetching Service Contract data are different. As per mail dated :23 March 2026 17:03 : Service Contracts Data Inclusion : Initial Invoice Transactions made on Service contracts will be available in Invoice 360 and it should not be considered. Instead, “Revenue Recognition” process will be carried out in LN for those invoices and get added to Sales GL. But the updates on those invoices(after revenue recognition process) will not be available in Invoice 360. To be discussed with Gokul on how it is currently considered in USA Sales Report in Power BI. After Internal discussion with Gokul, Added the Service Contracts details available from LN Table : LN_TSCTM400 with Filter Condition : STIN=20 27-04-2026: Observed that the above table does not include all Service Contract Transactions.Communicated via Mail to Joseph(LN ERP Team) to find out the root cause. 12-05-2026: Communicated to Gokul(LN ERP) to address the missing Service Contract invoices provided from venkatesh(Finance)
20 | All Pages | Service Contract Invoices are missing for Europe and Rotair | Open | 2026-04-27 |  | 12-05-2026: Communicated to Gokul(LN ERP) to address the missing Service Contract invoices provided from venkatesh(Finance)
21