## Instructions
| Project Name | Europe Sales Dashboard
| Project Manager | Krishna Raha
# | Field | Content
1 | Phase | Select from project lifecycle stages (e.g., Discovery, Initiation, Planning, Execution, Closure)
2 | Type | Idenifies a checklist as either a Process or Deliverable
3 | Checklist | Predefined list of processes and deliverables for each phase
4 | Categorization | Categorizes the activities against one of the six defined workstreams
5 | Owner | The individual accountable for completing/submitting the deliverable
6 | Required | Select from the drop-down: Yes (essential deliverables) or No (nice-to-have or conditional deliverables)
7 | Status | Select from the drop-down: Submitted, In-Progress, Not Applicable
8 | Comment | Additional notes such as submission date, dependencies, or reason for delay
9 | Key Stakeholders | RACI mapping of stakeholders against activities
| Status | G1- Discovery : Business and Functional Requirements Documentation in progress

## G1-Discovery
Key Stakeholders
# | Phase | Checklist Type | Checklist | Categorization | Owner | Required? | Status | Comment | Sponsor | PM | Business Lead | IT Lead | Architect | Vendor | Operations
1 | Discovery | Process | Have high-level business and functional requirements been documented? | Requirement Gathering & Design
2 | Discovery | Process | Has a preliminary business case with ROM cost vs. benefits been developed? | Business Delivery & Change Management
3 | Discovery | Process | Is the project aligned with business strategy and funding sources confirmed? | Program Management & Governance
4 | Discovery | Process | Has a high-level approach feasibility assessment been conducted with Enterprise/Solution Architect? | Requirement Gathering & Design
5 | Discovery | Process | Have key risks, dependencies, and constraints been identified? | Program Management & Governance
6 | Discovery | Process | Has an initial impact assessment (business process, systems, data) been completed? | Business Delivery & Change Management
7 | Discovery | Process | Are deliverables uploaded on SharePoint? | Program Management & Governance
8 | Discovery | Process | Steerco Deck to be reviewed before every meeting ? | Program Management & Governance
9 | Discovery | Deliverable | Business Requirement Document/Compliance /Security | Requirement Gathering & Design
10 | Discovery | Deliverable | High-Level approach Flow/Design/ Architecture | Requirement Gathering & Design
11 | Discovery | Deliverable | ROM Cost & Resource Estimates | Program Management & Governance
12 | Discovery | Deliverable | Business Case | Business Delivery & Change Management
13 | Discovery | Deliverable | Stage Gate Checklist | Program Management & Governance
Link to SharePoint for IT Elgi PPM Templates
|  |  | INSERT SCREENSHOT OF PMO APPROVAL RECEIVED OVER EMAIL |  |  | INSERT SCREENSHOT OF STEERCO APPROVAL RECEIVED OVER EMAIL

## G2-Initiation
Key Stakeholders
# | Phase | Checklist Type | Checklist | Categorization | Owner | Required? | Status | Comment | Sponsor | Business Lead | PM | IT Lead | Architect | Vendor | Operations
1 | Initiation | Process | Was a formal project kick-off held with all key stakeholders? | Program Management & Governance
2 | Initiation | Process | Were requirement gathering workshops conducted to finalize business, functional, and technical requirements? | Requirement Gathering & Design
3 | Initiation | Process | Has a Fit/Gap assessment (AS-IS vs TO-BE) been completed? | Requirement Gathering & Design
4 | Initiation | Process | Is business process documentation finalized and signed off? | Requirement Gathering & Design
5 | Initiation | Process | Has a data readiness assessment (quality, completeness, migration needs) been completed? | Data Management & Reporting
6 | Initiation | Process | Was a solution/vendor selection process (RFP/RFQ, scoring, demos) executed and documented? | Program Management & Governance
7 | Initiation | Process | If applicable, were Proof of Concepts conducted and results evaluated? | Build Test & Quality Assurance
8 | Initiation | Process | Has the project governance structure and cadence been defined and agreed? | Program Management & Governance
9 | Initiation | Process | Was IT Security engaged during infrastructure/software/vendor selection? | Deployment & Operations
10 | Initiation | Process | Have all mandatory deliverables for Initiation been completed and approved? | Program Management & Governance
11 | Initiation | Process | Are deliverables uploaded on SharePoint? | Program Management & Governance
12 | Initiation | Deliverable | Business Requirement Document-BRD | Requirement Gathering & Design
13 | Initiation | Deliverable | Technical Solution Document-TSD/HLD | Requirement Gathering & Design
14 | Initiation | Deliverable | Plan on a Page -POAP | Program Management & Governance
15 | Initiation | Deliverable | Stakeholder Register or RACI Matrix | Program Management & Governance
16 | Initiation | Deliverable | Project Costing & Resource Plan | Program Management & Governance
17 | Initiation | Deliverable | Project Charter | Program Management & Governance
18 | Initiation | Deliverable | Change Management Plan | Business Delivery & Change Management
19 | Initiation | Deliverable | Training Plan | Business Delivery & Change Management
20 | Initiation | Deliverable | Stage Gate Quality checklist | Program Management & Governance
Link to SharePoint for IT Elgi PPM Templates
|  |  | INSERT SCREENSHOT OF PMO APPROVAL RECEIVED OVER EMAIL |  |  | INSERT SCREENSHOT OF STEERCO APPROVAL RECEIVED OVER EMAIL

## G3-Planning & Design
Key Stakeholders
# | Phase | Checklist Type | Checklist | Categorization | Owner | Required? | Status | Comment | Sponsor | Business Lead | PM | IT Lead | Architect | Vendor | Operations
1 | Planning & Design | Process | Has the project organization, roles, and responsibilities been finalized? | Program Management & Governance
2 | Planning & Design | Process | Have detailed requirements been gathered and solution design signed off? | Requirement Gathering & Design
3 | Planning & Design | Process | Has the data cleansing and conversion plan been defined? | Data Management & Reporting
4 | Planning & Design | Process | Has the system integrations plan been prepared? | Requirement Gathering & Design
5 | Planning & Design | Process | Has the Project Plan (with timelines, milestones, and WBS) been developed and aligned with the core team? | Program Management & Governance
6 | Planning & Design | Process | Has the resource plan (people, infrastructure, software, other) been developed? | Program Management & Governance
7 | Planning & Design | Process | Has the Risk Register (RAID) been initiated and change control process established? | Program Management & Governance
8 | Planning & Design | Process | Has the change management plan been prepared? | Business Delivery & Change Management
9 | Planning & Design | Process | Is the communication plan set-up in place? | Business Delivery & Change Management
10 | Planning & Design | Process | Have vendors been engaged and draft contracts prepared? | Deployment & Operations
11 | Planning & Design | Process | Are deliverables uploaded on SharePoint? | Program Management & Governance
12 | Planning & Design | Deliverable | Project Organization & Governance Framework | Program Management & Governance
13 | Planning & Design | Deliverable | Approved Project Plan & WBS | Program Management & Governance
14 | Planning & Design | Deliverable | Technical Solution Document-TSD/LLD | Requirement Gathering & Design
15 | Planning & Design | Deliverable | Communication Plan | Program Management & Governance
16 | Planning & Design | Deliverable | RAID | Program Management & Governance
17 | Planning & Design | Deliverable | Stage Gate Checklist | Program Management & Governance
Link to SharePoint for IT Elgi PPM Templates
|  |  | INSERT SCREENSHOT OF PMO APPROVAL RECEIVED OVER EMAIL |  |  | INSERT SCREENSHOT OF STEERCO APPROVAL RECEIVED OVER EMAIL

## G4-Execute
Key Stakeholders
# | Phase | Checklist Type | Checklist | Categorization | Owner | Required? | Status | Comment | Sponsor | Business Lead | PM | IT Lead | Architect | Vendor | Operations
1 | Execute | Process | Has the detailed design, coding, and unit testing been completed in line with signed-off requirements? | Build Test & Quality Assurance
2 | Execute | Process | Has system integration testing (SIT) been conducted and all defects resolved? | Build Test & Quality Assurance
3 | Execute | Process | Have user training sessions been delivered and readiness feedback collected? | Business Delivery & Change Management
4 | Execute | Process | Has user acceptance testing (UAT) been completed with formal sign-off secured? | Build Test & Quality Assurance
5 | Execute | Process | Has data cleansing and conversion (trial runs, mock conversions, and final load) been executed successfully? | Data Management & Reporting
6 | Execute | Process | Has the IT stabilization and support plan been defined and aligned with all stakeholders? | Deployment & Operations
7 | Execute | Process | Have business KPIs (lead and lag indicators) for post-launch measurement been agreed upon? | Business Delivery & Change Management
8 | Execute | Process | Have open risks, issues, and deferred RAID items been reviewed and mitigated? | Program Management & Governance
9 | Execute | Process | Has the cutover plan (timelines, roles, rollback procedures) been finalized and tested? | Deployment & Operations
10 | Execute | Process | Have all planned deliverables for this phase been prepared and completed? | Program Management & Governance
11 | Execute | Process | Are deliverables uploaded on SharePoint? | Program Management & Governance
12 | Execute | Deliverables | UAT Test Plan/Executed UAT Test Scripts / Evidence/UAT Defect Log (resolved/closed)/Formal UAT Sign-off Document | Build Test & Quality Assurance
13 | Execute | Deliverables | Training Plan/Training Materials (slides, recordings, job aids)/ Training Completion Sign-off Email | Business Delivery & Change Management
14 | Execute | Deliverables | Change Management Plan/ Communication Plan with Timeline | Business Delivery & Change Management
15 | Execute | Deliverables | Data Migration Strategy/Data Mapping Document/Data Validation Sign-off | Data Management & Reporting
16 | Execute | Deliverables | Has the Cutover Plan been prepared and approved? | Deployment & Operations
17 | Execute | Deliverables | Detailed Cutover Plan/Cutover Task List & Owners/Cutover Schedule/Cutover Approval Sign-off | Deployment & Operations
18 | Execute | Deliverables | KPI Baseline Definitions/KPI Owner Sign-off | Business Delivery & Change Management
19 | Execute | Deliverables | Completed Gate Quality Checklist/Gate Approval Sign-off | Program Management & Governance
Link to SharePoint for IT Elgi PPM Templates
|  |  | INSERT SCREENSHOT OF PMO APPROVAL RECEIVED OVER EMAIL |  |  | INSERT SCREENSHOT OF STEERCO APPROVAL RECEIVED OVER EMAIL

## G5-Closure
Key Stakeholders
# | Phase | Checklist Type | Checklist | Categorization | Owner | Required? | Status | Comment | Sponsor | PM | Business Lead | Business SME | IT Head | IT Lead | IT Team | Architect | Vendor | Operations | Steering Committee
1 | Closure | Process | Has the post–go-live stabilization period been completed and steady-state support fully transitioned? | Deployment & Operations
2 | Closure | Process | Have benefits been measured against agreed KPIs (baseline vs. actual)? | Business Delivery & Change Management
3 | Closure | Process | Has formal stakeholder acceptance been secured for all project deliverables? | Program Management & Governance
4 | Closure | Process | Have linked transition/parallel projects been formally closed and archived? | Program Management & Governance
5 | Closure | Process | Was a lessons-learned workshop conducted and a retrospective documented? | Program Management & Governance
6 | Closure | Process | Has the final budget been reconciled and unused resources released? | Program Management & Governance
7 | Closure | Process | Have all project documents been archived for audit/compliance purposes? | Program Management & Governance
8 | Closure | Process | Is the Project Closure report prepared and signed-off by the project team? | Program Management & Governance
9 | Closure | Process | Are Project Handover documents shared with the relevant team and received their operations sign-off? | Deployment & Operations
10 | Closure | Process | Are all the planned trainings conducted? | Business Delivery & Change Management
11 | Closure | Process | Is the Change Management implemented as per plan? | Business Delivery & Change Management
12 | Closure | Deliverable | Post-Implementation Review Report/Benefits Realization Tracking Report | Business Delivery & Change Management
13 | Closure | Deliverable | Project Closure Report/Steering Committee Closure Approval / Sign-off/Closure Meeting Minutes | Program Management & Governance
14 | Closure | Deliverable | Stakeholder Feedback Survey Results/Stakeholder Satisfaction Report/Action Items / Recommendations | Business Delivery & Change Management
15 | Closure | Deliverable | Lessons Learned Document/Lessons Learned Session Minutes/Final Shared Repository Upload | Program Management & Governance
16 | Closure | Deliverable | Operations / Support Handover Document/Hypercare Plan/ Handover Acceptance Sign-off by Receiving Team | Deployment & Operations
17 | Closure | Deliverable | Completed Final Project Review Checklist/PMO Compliance Approval / Sign-off | Program Management & Governance
18 | Closure | Deliverable | Completed Gate Quality Checklist/Final Gate Approval Sign-off | Program Management & Governance
Link to SharePoint for IT Elgi PPM Templates
|  |  | INSERT SCREENSHOT OF PMO APPROVAL RECEIVED OVER EMAIL |  |  | INSERT SCREENSHOT OF STEERCO APPROVAL RECEIVED OVER EMAIL